## Gantt Chart
PROJECT:Online food delivery system
Project Title: BiteFlow
Project Manager: Omar Ahmed Soliman Soliman | [5 empty] | 23011370
ACTIVITY PLAN
| WEEK > | [7 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5
ID | Activity | Person name | ID | START date | END date | Days | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
1 | Project selection and agreement on tasks | All team members |  | 2026-04-24 | 2026-04-27 | 4 | 1 | 4 | 1 | 1 | 1 | 1
2 | Project Infos+Problem Description | Ibrahim Ali Khaled Ibrahim Ibrahim Elwakeel | 23010116 | 2026-04-27 | 2026-04-28 | 2 | 4 | 5 |  |  |  | 1 | 1
3 | System Objectives+Stakeholders | Abdulrahman Hamada Khairi | 23011314 | 2026-04-28 | 2026-05-01 | 4 | 5 | 8 |  |  |  |  | 1 | 1 | 1 | 1
4 | Functional Requirements+ Non-Functional gathering | Abdulrahman Mustafa Saeed Mohammed | 23012185 | 2026-05-01 | 2026-05-04 | 4 | 8 | 11 | [7 empty] | 1 | 1 | 1 | 1
5 | Requirements Analysis | Abdalla Mahmoud Saber Elsayed | 23011355 | 2026-05-04 | 2026-05-05 | 2 | 11 | 12 | [10 empty] | 1 | 1
6 | Use Case Diagram + Context Diagram | Aser Youssef Mohamed Elbadawy | 23012042 | 2026-05-05 | 2026-05-06 | 2 | 12 | 13 | [11 empty] | 1 | 1
7 | Activity Diagram + State Machine Diagram | Omar Mostafa Ali | 23011390 | 2026-05-05 | 2026-05-07 | 3 | 12 | 14 | [11 empty] | 1 | 1 | 1
8 | Collecting and verifying documents for project management and creating Gantt charts and PERT charts. | Omar Ahmed Soliman Soliman | 23011370 | 2026-05-09 | 2026-05-10 | 2 | 16 | 17 | [15 empty] | 1 | 1
| Actual Total activity time (without gathering documents(last Activity)) |  |  |  |  | 21 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35

## pert chart
Expected Time rule | TE=(O+4M+P)/6
| previous activity | Activity | Activity ID | TE | O | M | P | LS | LF | EF | ES | slack
| Null | Project selection and agreement on tasks | A | 2 | 1 | 2 | 3 | 0 | 2 | 2 | 0 | 0
| A | Project Infos+Problem Description | B | 2 | 2 | 2 | 4 | 2 | 4 | 4 | 2 | 0
| B | System Objectives+Stakeholders | C | 2 | 1 | 2 | 4 | 4 | 6 | 6 | 4 | 0
| C | Functional Requirements+ Non-Functional gathering | D | 3 | 3 | 3 | 5 | 6 | 9 | 9 | 6 | 0
| D | Requirements Analysis | E | 2 | 1 | 2 | 4 | 9 | 11 | 11 | 9 | 0
| E | Use Case Diagram + Context Diagram | F | 3 | 2 | 3 | 5 | 11 | 14 | 14 | 11 | 0
| E | Activity Diagram + State Machine Diagram | G | 3 | 2 | 3 | 5 | 11 | 14 | 14 | 11 | 0
|  |  |  | Total duration | 14
|  |  |  | conclusion | all activity is in critical path (this makes sense )
ES=4
EF=6
C
LS=4
0
LF=6
ES=6
EF=9
D
LS=6
0
LF=9
ES= 0
EF=2
A
LS=0
0
LF=2
ES=2
EF=4
B
LS=2
0
LF=4
ES=9
EF=11
E
LS=9
0
LF=11
ES=11
EF=14
F
LS=11
0
LF=14
ES=11
EF=14
G
LS=11
0
LF=14